## Product Backlog- Team Kaprekar
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | Complexity | Risk/ Impact(L-Low, M- Medium, H-High) | Type | Comments
1 | 1 |  | M | Us:101 | Customer must create his Account | Very Simple | L | Functional
2 | 2 |  | M | Us:102 | Customer must login into the application | Complex | M | Functional
3 | 3 |  | M | Us:103 | Customer can check insert pickup and delivery address | Very Simple | L | Technical
4 | 4 |  | M | Us:104 | Customer can make a the courier is booked automatically | Very Simple | L | Technical
5 | 5 |  | M | Us:105 | Customer can view the booking status ans see the approx date of pickup and delivery date | Complex | L | Functional
6 | 6 |  | M | Us: 201 | Head manager can log in and regiter in the application | Complex | H | Functional
7 | 7 |  | M | Us: 202 | Head manager can add centers | Complex | L | Technical
8 | 8 |  | M | Us: 203 | Head manager can delete the centers | Average | L | Technical
9 | 9 |  | M | Us: 204 | Manager can register and log in | Average | L | Technical
10 | 10 |  | S | Us: 205 | Manager can update the status of the courier | Very Simple | L | Technical
11 | 11 |  | S | Us: 206 | Manager can also add the delivery boy | Very Simple | L | Technical
12 | 12 |  | S | Us: 207 | Delivery boy can log in and register | Very Simple | L | Technical
13 | 13 |  | W | Us: 301 | Delivery boy can change the status of courier Booked, Picked up, On the Way, Delivered | Very Simple | L | Non-Functional
14 | 14 |  | W | Us: 302 | Delivery boy can deliver the pacakge | Very Simple | L | Non-Functional
15 | 15 |  | W | Us: 303 | Head manager can also add manager for particular center | Very Simple | L | Non-Functional
16 | 16 |  | W | Us: 304 | Customer can check the status for his order | Very Simple | L | Non-Functional
17 | 17 |  | W | Us: 305 | Manager can not add Head Manager | Very Simple | L | Non-Functional
18 | 18 |  | M | Us: 208 | All the Users can logout after log in | Simple | L | Technical
19 | 19 |  | M | Us: 306 | Authentication of the Customer(Valid/Invalid User) | Average | L | Functional
20 | 20 |  | M | Us: 209 | Head Manager can add/modify Manager and Center | Average | M | Technical

## Sprint Backlog- Team Kaprekar
Product Backlog ID | Task Step description | Assigned to | Assigned Date | Completed Date | Adjusted estimate | Status | Actual Effort | Comment
P:101 | Create POJO class for Booked Courier | Niraj | 2022-08-29 | 2022-08-29 |  | Done
P:102 | Create POJO class for Center | Niraj | 2022-08-29 | 2022-08-29 |  | Done
P:103 | Create POJO class for Customer | Niraj | 2022-08-29 | 2022-08-29 |  | Done
P:104 | Create POJO class for Delivery Boy | Varun | 2022-08-29 | 2022-08-29 |  | Done
P:105 | Create POJO for Head Manager | Varun | 2022-08-29 | 2022-08-29 |  | Done
P:106 | Create POJO class for Manager |  | 2022-08-30 | 2022-08-30 |  | Done
P:107 | Make Database and apply annotation and all required validation in POJO class of Booked Courier | Niraj | 2022-08-30 | 2022-08-30 |  | Done
P:107 | Make Databse and apply annotation and all required validation in POJO class of Center | Niraj | 2022-08-30 | 2022-08-30 |  | Done
P:108 | Make Databse and apply annotation and all required validation in POJO class of Customer | Varun | 2022-08-30 | 2022-08-30 |  | Done
P:109 | Make Databse and apply annotation and all required validation in POJO class of Delivery Boy | Varun | 2022-08-30 | 2022-08-30 |  | Done
P:110 | Make Databse and apply annotation and all required validation in POJO class Head Manager | Niraj | 2022-08-30 | 2022-08-30 |  | Done
| Make Databse and apply annotation and all required validation in POJO class Manager | Varun | 2022-08-31 | 2022-08-31
P:111 | Booked Courier
| Controllers | Varun | 2022-09-01 | 2022-09-04 |  | Done
| Services | Varun | 2022-09-01 | 2022-09-04 |  | Done
| Repositoty | Varun | 2022-09-01 | 2022-09-04 |  | Done
P:112 | Center
| Controllers | Varun | 2022-09-01 | 2022-09-04 |  | Done
| Services | Varun | 2022-09-01 | 2022-09-04 |  | Done
| Repositoty | Varun | 2022-09-01 | 2022-09-04 |  | Done
P:113 | Customer
| Controllers | Poojitha | 2022-09-01 | 2022-09-04 |  | Done
| Services | Poojitha | 2022-09-01 | 2022-09-04 |  | Done
| Repositoty | Poojitha | 2022-09-01 | 2022-09-04 |  | Done
P:114 | Head Manager
| Controllers | Niraj | 2022-09-01 | 2022-09-04 |  | Done
| Services | Niraj | 2022-09-01 | 2022-09-04 |  | Done
| Repositoty | Niraj | 2022-09-01 | 2022-09-04 |  | Done
P:115 | Manager
| Controllers | Avanti | 2022-09-01 | 2022-09-04 |  | Done
| Services | Avanti | 2022-09-01 | 2022-09-04 |  | Done
| Repositoty | Avanti | 2022-09-01 | 2022-09-04 |  | Done
P:115 | Delivery Boy
| Controllers | Niraj | 2022-09-01 | 2022-09-04 |  | Done
| Services | Niraj | 2022-09-01 | 2022-09-04 |  | Done
| Repositoty | Niraj | 2022-09-01 | 2022-09-04 |  | Done
| Exceptions | Varun | 2022-09-07 | 2022-09-07 |  | Done
P: 201 | Creating React app and installing the necessary tools | Varun | 2022-09-10 | 2022-09-10 |  | Done
|  | Niraj | 2022-09-10 | 2022-09-10 |  | Done
P:202 | Components
| Landin Page | Varun | 2022-09-10 | 2022-09-12 |  | Done
| Login | Niraj | 2022-09-10 | 2022-09-12 |  | Done
| Header | Avanti | 2022-09-10 | 2022-09-12 |  | Done
| Footer | Poojitha | 2022-09-10 | 2022-09-12 |  | Done
| Head Manager | Niraj | 2022-09-10 | 2022-09-12 |  | Done
| Nav Bar | Varun | 2022-09-10 | 2022-09-12 |  | Done
| Registration | Niraj | 2022-09-10 | 2022-09-12 |  | Done
| View Profile | Niraj | 2022-09-10 | 2022-09-12 |  | Done
| Booked Courier | Varun | 2022-09-10 | 2022-09-12 |  | Done
| Customer Home | Varun | 2022-09-10 | 2022-09-12 |  | Done
| Manager List | Varun | 2022-09-10 | 2022-09-12 |  | Done
| Center Registration | Niraj | 2022-09-10 | 2022-09-12 |  | Done
P: 203 | Services
| BookedCourier Service | Niraj | 2022-09-12 | 2022-09-13 |  | Done
| Center Service | Niraj | 2022-09-12 | 2022-09-13 |  | Done
| Delivery Boy Service | Niraj | 2022-09-12 | 2022-09-13 |  | Done
| Head ManagerService | Varun | 2022-09-12 | 2022-09-13 |  | Done
| Manager | Varun | 2022-09-12 | 2022-09-13 |  | Done
| Customer Service | Varun | 2022-09-12 | 2022-09-13 |  | Done
P: 204 | Integration of Frontend with Backend | Varun | 2022-09-13 | 2022-09-13 |  | Done
|  | Varun | 2022-09-13 | 2022-09-13 |  | Done
|  | Niraj | 2022-09-13 | 2022-09-13 |  | Done